| Leadership Group: Information Technology Steering Committee |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Department: Information Technology |  |  |  |  |  |  | Division: Technical Systems and Networking |  |  |
| ### Project Sponsor: Phil Bertolini |  |  | Date Requested: Oct 14, 2003 |  |  |  |  | PM Customer No. 186 |  |
| Request Type: xx New Development Enhancement #### Maintenance Customer Support |  |  |  |  |  |  |  |  |  |
| IT Team Name: Technical Services |  |  |  |  |  | IT Team No: 6 |  |  |  |
| Project Manager/Leader: Norma Miller |  |  |  |  |  |  |  |  |  |
| Account Number: | 17030 | Account Description: |  | Technical Systems and Networking |  |  |  | Customer Name: | Information Technology |
| Grant Funded? Yes No xx |  |  |  |  | Mandate? Yes No xx Mandate Source: |  |  |  |  |

Project Goal

To design and build a thin client architecture so that the total cost of ownership of 285 users will be achieved by May 14, 2004.

Business Objective

Thin Client Computing Pilot will procure technical consulting assistance and with the selected consultant will define and document an infrastructure architecture, build a test environment, build a production environment, and convert 285 PC computer users to the new, thin client architecture.

Major Deliverables

- (OC) Work Plan, Issues Log, Status Reports

- (OC) Professional Services Request for Proposal and Contract Award

- (OC) Computer Usage Matrix

- (OC) Marketing/Communication Plan

- (Vendor) Infrastructure Assessment Document

- (Vendor) Metaframe Architecture Document

- (Vendor and OC) Configured test and production environments

- (OC) Help Desk Materials

- (Vendor) Thin Client Cut-Over Report (for first 100 pilot users converted to thin client)

- (OC) Thin Client Cut-Over Report (for remaining 180 pilot users converted to thin client)

- (Vendor and OC) Lessons Learned

- (Vendor and OC) Phase 1 Planning Documentation

Approach

Oakland County project staff will work hand-in-hand with the selected professional-services contractor staff to design and build the thin client architecture.  The selected professional-services contractor will be responsible for submission of deliverables identified above.   Oakland County will be responsible for review and acceptance of vendor deliverables.

Benefits

Return on

Investment (ROI)

Please see attached Return on Investment analysis.

Revenue/

Cost Recovery

Please see attached Return on Investment analysis.

Intangible

Improved Service

The delivery of thin client architecture provides Oakland County with the opportunity for more timely upgrades to standard, office automation tools.  It also provides for more secure and backed-up user data and simplifies the PC desktop environment.

Product/Service

Accuracy

Please see Thin Client Computing Proposal.

Product/Service

Productivity

Please see attached return on investment analysis.

Impact

Number of Users

- Convert 285 pilot user desktops to the thin client architecture.

Divisions

- Pilot user desktops and departments will be determined as part of the work executed in the Thin Client Computing work plan.

- All Oakland County departments will be affected by conversion to thin client architecture.

Leadership Groups

- All leadership groups will be affected by the Thin Client Computing project.

- This project will need to be approved by the Information Technology Steering Committee.

Risk

Business Environment: 	Medium – Project will require some changes to existing business processes.

Technical Environment: 	High – Previously implemented technologies with new aspects and/or new requirements.

Assumptions

Staffing	Resources will be available for the hours indicated per the attached project plan.  The following roles and resources’ availability will be as follows:

| Role: | # Name | Hours per Day |
| --- | --- | --- |
| Project Sponsor: | Phil Bertolini David Veit | As Needed As Needed |
| Project Manager: | Norma Miller | 5.9 hours/day |
| Data Base Administrator: | Not Required | Not Applicable |
| Source System Expert: | Harshika Patel Kevin Bertram Joe Tabor Romel Llarena | 4.4 hours/day 4.4 hours/day 4.4 hours/day 5.9 hours/day |
| Business Analyst: | Karla Early Kim Morris Lisa Schmidt Vickie Worrell Jamarice Simpson Sandy Jaszczak Salina Rivera | 2.1 hours/day 4.4 hours/day 4.4 hours/day 5.9 hours/day 5.9 hours/day 4 hours/day 4 hours/day |
| Programmer/Analyst: | Robert Carroll Joe Hickey Jim Burton Leon Walker Sue Hsich | 5.9 hours/day 5.9 hours/day 5.9 hours/day 5.9 hours/day 2 hours/day |

Facilities

This project requires securing office space (desks, PC’s, telephones) for up to

two full-time professional services contractor staff and two full-time help desk contractor staff for a period of up to three months.

Technical

This project requires the purchase of new production hardware and software.

This activity is planned for in the project plan.  However, the timeframe for when the equipment is purchased and when it is needed for installation is only six weeks.  Delay in receiving production hardware could impact schedule.

This project requires the purchase of 12 pilot Citrix servers and 13 phase 1citrix servers. Eight of the twelve pilot servers will use eight of the servers purchased for the portal project.

Funding

Board of Commissioners Resolution 03138.

Other

This project requires Technical Services staff to obtain Citrix certification training prior to the start of design activities.

Current CSA customer service level commitment is 2 weeks.  During the months of September and October 2002, no commitment beyond first come, first serve will be made to customers and “emergency” requests will need to be prioritized.

Priority

00

Constraints

Selected pilot users to have desktop converted to thin client architecture must use Office Automation products and/or mainframe only.

Pilot users will be selected from the group of Oakland County staff that currently use the old Gateway and Intergraph PCs.

Thin client devices will be limited to 1 Gigabyte storage per user.  Part of the thin client design activities will identify a strategy for data archival.  The thin client pilot assumes that pilot users will use existing PC capability for archival needs.

Exclusions

None identified.

PROJECT PHASE AUTHORIZATION

| Phase(s): Project Management, Thin Client Phase 1 |  |
| --- | --- |
| Total Estimated Systems Development Hours: 20 Cost: $ 2,160 |  |
| Total Estimated Internal Services Hours: 361 Cost: $ 40,134 |  |
| Total Estimated Technical Systems Hours: 3,161 Cost: $ 145,967 |  |
| Total Estimated DISC Hours: 295 Cost: $ 22,125 |  |
| Total Estimated CLEMIS Hours: Cost: |  |
| IT Systems Development Division Manager Approval: | Date: |
| IT Technical Systems Division Manager Approval: | Date: |
| IT DISC Division Manager Approval: | Date: |
| IT CLEMIS Division Manager Approval: | Date: |
| IT Resource Manager Approval: | Date: |
| IT Resource Manager Approval: | Date: |
| IT Resource Manager Approval: | Date: |
| IT Resource Manager Approval: | Date: |
| IT Resource Manager Approval: | Date: |
| IT Management Approval: |  |
| Approved: Yes No | Date: |
| Reason: |  |
| Project Sponsor Approval: |  |
| Title: | Date: |

PROJECT SUMMARY

(T63010TC) Authorized Systems Development (see above) Hours: 3,837 Cost: $ 210,386

(T64010TC) Preliminary Estimated Systems Development for Future Phases Hours: 4,977 Cost: $ 226,545

Grand Total Estimated Systems Development Hours: 8,814 Cost: $ 436,931

PROJECT COMPLETION AUTHORIZATION

| Customer Acceptance of Product: |  |
| --- | --- |
| Title: | Date: |
| Project Office Review: | Date: |